## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload audio files so that they can be analyzed | Must | Customer chat data / file input | Divya | Done
Sprint 1 | Sprint 1 | US-02 | As a user, I want to view uploaded audio and basic details | Must | Audio upload module + STT integration | Divya | Done
Sprint 2 | Sprint 2 | US-03 | As a system, I want to convert audio into text using speech-to-text | Must | Whisper / Speech-to-text model | Pranathi | Done
Sprint 2 | Sprint 2 | US-04 | As a system, I want to analyze text using AI for quality insights | Must | Prompt design + LLM API | Pranathi | Done
Sprint 3 | Sprint 3 | US-05 | As a system, I want to retrieve relevant context using RAG to improve analysis | Must | Knowledge base + vector retrieval | Jack | Done
Sprint 3 | Sprint 3 | US-06 | As a system, I want to generate scores and feedback based on conversation | Should | RAG output + LLM analysis | Jack | In Progress
Sprint 3 | Sprint 3 | US-07 | As a user, I want to see summary and insights of the conversation | Should | AI output data | Divya | In Progress
Sprint 4 | Sprint 4 | US-08 | As a user, I want filters (agent, issue type, date) for better analysis | Should | Dashboard data + scoring results | Divya | In Progress
Sprint 4 | Sprint 4 | US-09 | As a user, I want to export reports in PDF/Excel format | Should | Dashboard UI + processed results | Pranathi | To Do
Sprint 4 | Sprint 4 | US-10 | As a system, I want to deploy the application for final usage | Must | All modules completed | Jack | To Do
d
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 127 | 29 | 27 | 25 | 16 | 6 | 8 | 3 | 1 | 3 | 2 | 3 | 2 | 2 | 1
SPRINT 1 BACKLOG
US-01 | T-101 | Setup project repo and basic UI layout | 2026-02-04 | 2026-02-06 | Divya | Setup | Completed | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
US-02 | T-102 | Implement audio upload functionality | 2026-02-10 | 2026-02-15 | Divya | Development | Completed | 8 | 1 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-02 | T-103 | Display uploaded audio details | 2026-02-24 | 2026-02-25 | Divya | Testing | Completed | 5 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
US-01 | T-104 | Initial UI testing and validation | 2026-02-25 | 2026-02-28 | Divya | Documentation | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-03 | T-201 | Integrate speech-to-text model (Whisper) | 2026-03-01 | 2026-03-04 | Pranathi | Development | Completed | 8 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
US-03 | T-202 | Process and clean transcript data | 2026-03-05 | 2026-03-08 | Pranathi | Development | Completed | 6 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
US-04 | T-203 | Design AI prompt for analysis | 2026-03-09 | 2026-03-11 | Pranathi | Design | Completed | 7 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-04 | T-204 | Implement AI analysis pipeline | 2026-03-12 | 2026-03-14 | Jack | Development | Completed | 9 | 2 | 2 | 2 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-205 | Validate AI outputs | 2026-03-15 | 2026-03-17 | Jack | Testing | Completed | 6 | 2 | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-05 | T-301 | Prepare knowledge base for RAG | 2026-03-17 | 2026-03-17 | Jack | Preparation | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-302 | Implement RAG retrieval logic | 2026-03-17 | 2026-03-17 | Jack | Development | Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-303 | Generate scoring and feedback | 2026-03-17 | 2026-03-17 | Jack | Development | In Progress | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-304 | Display summary and insights UI | 2026-03-17 | 2026-03-17 | Divya | Frontend | In Progress | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-305 | Add filters to dashboard | 2026-03-17 | 2026-03-17 | Divya | Frontend | To Do | 7 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-09 | T-401 | Generate PDF/Excel reports | 2026-03-18 | 2026-04-18 | Pranathi | Development | To Do | 8 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-402 | Setup deployment environment | 2026-03-19 | 2026-03-19 | Pranathi | Development | To Do | 7 | 2 | 2 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-403 | Add logging and monitoring | 2026-03-19 | 2026-03-19 | Jack | Backend | To Do | 6 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-404 | Final testing and debugging | 2026-03-19 | 2026-03-19 | All | Testing | To Do | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Audio upload UI not aligning properly | Fixed UI layout using proper components
Sprint 1 | Day 5 | Audio file format issues during upload | Added validation for file type
Sprint 2 | Day 3 | Transcription accuracy was low | Improved preprocessing and audio cleaning
Sprint 2 | Day 6 | AI output was inconsistent | Refined prompt structure and examples
Sprint 3 | Day 2 | RAG retrieval not giving relevant results | Improved vector retrieval logic and filtering
Sprint 3 | Day 5 | Delay in API response during analysis | Optimized backend API calls
Sprint 4 | Day 3 | Dashboard loading slowly | Implemented caching for faster loading
Sprint 4 | Day 7 | Export report formatting issues | Fixed layout and tested with sample data
Sprint 4 | Day 9 | Duplicate alerts triggered in system | Added cooldown logic for alert handling

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-04 | 2026-03-04 | Divya | Plan UI structure before coding | Random UI changes | Team discussions | Created consistent UI layout
2 | Sprint 1 | 2026-02-05 | 2026-02-05 | Pranathi | Organize backend modules clearly | Mixing logic in single file | Writing modular code | Structured backend pipeline
3 | Sprint 1 | 2026-02-09 | 2026-02-12 | Jack | Break AI tasks into smaller parts | Direct full implementation | Step-by-step testing | Improved development flow
4 | Sprint 2 | 2026-02-16 | 2026-02-18 | Pranathi | Improve transcription preprocessing | Using raw audio directly | Testing outputs regularly | Enhanced transcription accuracy
5 | Sprint 2 | 2026-02-23 | 2026-02-25 | Jack | Refine AI prompts carefully | Using generic prompts | Prompt tuning | Improved AI response quality
6 | Sprint 2 | 2026-02-28 | 2026-03-03 | Divya | Improve UI interaction flow | Ignoring UX issues | Feedback-based updates | Enhanced user experience
7 | Sprint 3 | 2026-03-04 | 2026-03-06 | Jack | Implement RAG step-by-step | Using AI without context | Retrieval optimization | Improved AI accuracy using RAG
8 | Sprint 3 | 2026-03-08 | 2026-03-11 | Divya | Prepare dashboard structure early | Late UI changes | UI consistency | Faster dashboard development
9 | Sprint 3 | 2026-03-15 | 2026-03-17 | Pranathi | Optimize backend API calls | Unoptimized API calls | Code debugging | Reduced response time
10 | Sprint 4 | 2026-03-18 | 2026-03-20 | Jack | Plan deployment steps early | Last-minute deployment | Testing before release | Smooth deployment process
11 | Sprint 4 | 2026-03-22 | 2026-03-23 | Pranathi | Monitor backend errors | Ignoring minor issues | Logging and debugging | Improved system stability
12 | Sprint 4 | 2026-03-23 | 2026-03-23 | Divya | Finalize UI for reports | Changing design frequently | UI polishing | Improved report presentation